## Sheet1
|  |  |  | Tasks to trace | 7.0: target now 22
25020
18981 |  | ? | m4 | Display environment.xml
18943 |  | v7.0 | m | WUQuery: LastNDays | Waiting for review
18940 |  |  |  | WUQueryGetGraph returns empty response | Waiting for subtask
18740 |  | v7.0 |  | Timings table row order | Waiting for Gavin
18655 |  | v7.0 |  | ESP Cache (design) | Design with Tony
18609 |  | v7.0 |  | ESP mishandling unauthenticated soap requests | Verified with Rodrigo and 401 was sent.
18252 |  | v7.0 | m4 | No way to access roxie summary stats for a query
18105 |  | 7.0? | next | Double click on logical file not work for query files with packagemap | Design with Tony
17921 |  | v7.0 | m/h17921 | memcached | (Encrypt wait for Russ)
16776 |  | v7.0 |  | TOO many files message | Design with Miguel
16664 |  | v7.0 | m2 | WU error reporting (subtasks, not UI) | Implement email notification and create JIRA.
16653 |  | v7.0 | m3 | JBuff: Exceeded maximum size creating ZAP file | Check CURL HTTP headers for streaming (chuck)
16332 |  |  |  | Log in to ECL Watch without Feature permission error message could be better
11621 |  | v7.0 | dup | logout | Wait for docs
18846 |  | v7.0 |  | Retrieve environment name | blocked by 18845
16335 |  | v7.0 | next | Remove ESP services no longer in use | Design with Tony: wsdops (ananth: can remove), wssvn, ws_dispatch - yma? ws_roxiequerystat? ws_thing_finder (stu: not used anymore)?
16233 |  | v7.0? |  | Add grep feature to filter only specific rows of roxie log. | Implement in Log Virtualization tool? See Miguel's comment for HPCC-14890
16152 |  | v7.0? | wait | Ability to retrieve previous runs of "same" workunit | Waiting for comment
12372 |  | v7.0 | wait UI | Add a page/area to Eclwatch for admins to see runtime information, e.g. locks/clients | wait UI
11822 |  | v7.0? | m2 | Esp->Sasha inefficient access to archived workunits for pages>1 | Waiting for review
18654 | kw |  | next | encapsure (Wait 18517)
18396 |  | ? | next | extend esp status control (wait 18400 - may do subtask)
18352 |  | ? | next | ZAP decode graph progress
14676 |  | v8.0 |  | user based calls
18099 | kw |  | 8.0? | Replace hard coded URLs in session management code | 8.0?
17969 | kw |  | 8.0? | Check soap security headers and HTTP security at the same place | 8.0?
17886 | kw |  | m5 | Create WsWorkunits.WUECLQueryAction method | Waiting for review
17819 |  |  |  | Why was the problem with an invalid wuid not caught. | ?
17551 |  |  |  | Cannot upload file when LZ is not configured correctly. | Not sure how to fix
17334 | kw |  | 8.0? | Detect and correct wrong dropzone path in FileSpray services | 8.0?
17333 | kw |  | 8.0? | Refactor TpWrapper code to minimize the apparent code duplication/maintainability | 8.0?
17164 |  |  |  | Count files with filters? | Is what we need?
16975 |  |  |  | Create local work unit from ZAP | Not sure how it works. How to add related data files into a local machine.
16344 | kw |  |  | Protect/unprotect files from wsdfu | Not sure how to do if no security (no owner - no userid).
16324 |  |  |  | WSAttribute function to change attribute type | David?
16312 |  |  | done? | esploggingservice does not perform feature level auth | done?
16074 |  |  | 8.0? | Support Rootless array in ECM | 8.0?
15424 |  |  |  | ECLWatch Playground displays two results when only one is relevant. | Not sure how to fix
14994 | kw |  |  | Protect/unprotect files from ECLWatch | See HPCC-16344
14659 |  |  |  | FilesInUse Sometimes Inaccurate | Can't reproduce
14542 |  |  |  | Add ability to unprotect a workunit | For Gavin? a mechanism to easily via ECL code to unprotect a large number of WU's
14391 |  |  | 8.0? | How to display thor on spares (in preflight?) | 8.0?
14312 | kw |  |  | Improve Xref | 8.0?
13902 | kw |  | 8.0? | Better WsDfu method to view data file and schema | 8.0?
13499 |  |  |  | Download filtered results for Logical files, Workunits, Queries | Still need?
13425 |  |  |  | Eclwatch Unable to get property 'refreshXGMML' from WUGetGraph | Not sure if it is still an issue
13367 |  |  |  | ECLWatch legacy mode allows user to view/change file scopes | Still need?
12757 |  |  |  | Allow SOAP requests to be compressed (over http) | Still need?
12550 |  |  |  | FilesInUse Sometimes Inaccurate | Can't reproduce. Not sure how to fix
12135 |  |  |  | shared environment xml file showing all servers on ecl watch page | Still need? Blocked by H11733
11783 |  |  |  | WsWorkunit/WUInfo ECLResults Should Include NodeGroup | Blocked by H11733
11512 |  |  |  | FileSpray.GetDFUWorkunit, Missing GroupName | Not sure how to fix
11185 |  |  |  | Add option for data removal based on package map with ECLwatch | Still need?
11184 |  |  |  | Support URL for adding package maps to ECLwatch | Still need?
10988 | kw |  | 8.0? | Refactor code for doWUQueryWithSort/addWUQueryFilter in WsWorkunits | 8.0?
9829 | kw |  |  | Create a generalized method for sorting EclWUs and querysetqueries | Still need?
9538 |  |  |  | get more detailed or definitive updates to xref status | Not sure how to fix
9282 |  |  |  | Feature Request - New WsDFU service | Still need?
8198 |  |  |  | Verify that environment.xml files match on all nodes | 8.0?
2065 |  |  |  | Remove references to SMC in ECL Watch Permissions area | Still need?
1645 |  |  | 8.0? | Compare WU result | 8.0? Wait for Gordon
17810 | kw |  |  | Force ESP cache | invalid
17406 |  |  |  | WSDFU doesn't sent responses to AddtoSuperfile requests - HPCC | Can't reproduce
17184 |  |  |  |  | User error
17081 |  |  |  | ZAP fails to download, Mac OS X 10.10.5 Safari 10.0.3 | Can't reproduce
16894 |  |  |  | ZAP report should include a portion of log which is relevant. | The existing ZAP report only contains the portions of logs which is related to that WU
16793 |  |  |  | Eclwatch to ignore /run and /sys folders | User error
16641 |  |  |  | Eclagent queue unpauseable via the ECL Watch interface | Can't reproduce
16494 |  |  |  |  | Can close
16402 |  |  |  |  | Can close
16214 |  |  |  | Super files appear blank, if there are foreign subfiles that are missing | Can't reproduce
16069 |  |  |  | Unable to open graphs on 5.6 ECL watch and IDE for 6.0 ECL Wus | known limitation
15959 |  |  |  | .XLS links are downloading blank documents from the WU outputs | Download csv file' has been implemented to replace old xls option.
15869 |  |  |  | generated ZAP report contains excerpt from all system log file | Can close
15207 |  |  |  | Dynamic control of which TxSummary milestones are logged | Txsummary has been revised to meet the requirements.
15195 |  |  |  | esp in dataland were very slow rendering activitiy | Can't reproduce
15185 |  |  | dup | Alpha Prod Logical Files wont load and displays a 'out of memory' error | Fixed
15051 |  |  |  | logical file locked by cluster it isn't on | Can't reproduce
14838 |  |  |  | ensure that all file browsing capabilities in Legacy ECLWatch are in new ECL Watch.
14311 | kw |  |  | Cache preflight response | invalid (ESP has cache function)
14222 |  |  |  | Unicode bug whenever using view data file in LF Browser | only happens in legacy ECLWatch
13575 |  |  |  | File tab search does not work properly | Can't reproduce
13143 | kw |  |  | Increase default_client_version for ECLWatch to use latest revision | invalid
11171 |  |  |  | open packagemap details function broken | Can't reproduce
|  |  | m4 | unittests_sasha